LAST-MILE DELIVERY OPERATIONS CASE STUDY

Last-Mile Delivery Throughput Optimization Program

A DMAIC-informed program design using transparent synthetic operations data

Vishvanath Naik  |  August 2026

Evidence disclosure: Meridian Logistics Network is fictional. Public sources provide selected context only. The dataset contains 7,450 synthetic van-level observations. Operational results and financial benefits are formula-derived model outputs, not employer results.

# Executive Summary

This case study shows how a program manager could diagnose and address a peak-window dock constraint across five fictional delivery stations. The work combines process design, van-level analysis, a six-week pilot, phased rollout governance, a component-based benefits model, and a control mechanism.

The modeled network moves from 14.60 to 11.39 minutes per van, a 22.0% reduction. On-time dispatch rises from 80.2% to 95.6%. The theoretical throughput-capacity gain is 28.2% before utilization and other constraints. These results come from synthetic observations and demonstrate the analysis method, not a completed operational achievement.

| Outcome | Baseline | Post rollout | Interpretation |
| --- | --- | --- | --- |
| Dock-to-departure time | 14.60 min | 11.39 min | 22.0% lower |
| On-time dispatch | 80.2% | 95.6% | 15.4 percentage-point increase |
| Failed-package rate | 5.08% | 3.28% | Guardrail improved in the model |
| Overtime per route | 20.9 min | 10.0 min | 52.2% lower |
| Year 1 net benefit | Not applicable | $406K | Base case after implementation costs |

Decision: Adopt the standardized peak flow in the modeled network, subject to local safety sign-off, weekly guardrail review, and validation of financial assumptions with Operations and Finance.

# 1. Define

## Problem and Goal

Peak-window staging and scanning create a serial queue that delays departure and increases overtime, rescue activity, and delivery reattempt risk. The program goal is to reduce average dock-to-departure time by at least 20% and reach at least 95% on-time dispatch within 16 weeks.

Staffing boundary: The intervention uses two existing, cross-trained employees reassigned during the peak window. It does not add net headcount. The financial model includes an opportunity cost for that reassignment.

## Scope and Guardrails

| Area | Included | Excluded |
| --- | --- | --- |
| Process | Staging, scanning, loading, and dispatch | Route optimization after departure |
| Network | Five fictional delivery stations | Line-haul and fulfillment-center operations |
| Time | 6:00 to 9:00 peak window | Non-peak shift redesign |
| Guardrails | Safety, scan quality, missing packages, labor hours | Unvalidated customer-experience attribution |

## Customer and Business Measures

On-time dispatch is the primary critical-to-quality measure. It is a leading operational indicator, not a substitute for customer on-time delivery. A production study would quantify the relationship between departure delay and the customer promise before claiming downstream customer impact.

## RACI

| Role | Design | Pilot | Go / No-Go | Rollout | Control |
| --- | --- | --- | --- | --- | --- |
| Central Operations Director | C | C | A | I | I |
| Program Owner | R | R | R | R | R |
| Station Operations Managers | C | R | C | R | R |
| IT / Scanning Systems | C | R | C | R | C |
| Safety and Compliance | C | C | C | C | I |

The Central Operations Director is the single accountable owner for the go/no-go decision. The Program Owner is responsible for preparing the decision, managing execution, and closing escalations.

# 2. Measure

## Dataset and Operational Definitions

The revised workbook contains 7,450 deterministic synthetic van-level records: 3,200 baseline observations, 1,050 pilot observations at Station Alpha, and 3,200 post-rollout observations. Each record includes five process-stage times, departure delay, packages, stops, failed packages, overtime, lane count, and a data-quality flag.

| Metric | Operational definition | Unit |
| --- | --- | --- |
| Dock-to-departure time | Sum of five measured process stages | minutes per van |
| On-time dispatch | Departure delay is zero or negative | rate |
| Failed-package rate | Failed packages divided by packages handled | rate |
| Overtime | Peak-window labor beyond scheduled time | minutes per route |

Measurement boundary: Synthetic timestamps are reconciled to stage totals. A live implementation would also test scanner clock synchronization, missing events, duplicate scans, and agreement with manual observations.

# 3. Analyze

## Stage Contribution

The synthetic baseline assigns the largest portion of dock time to the staging queue. This supports a testable mechanism: one active lane, arrival-order loading, no real-time queue trigger, and no standardized peak response create a serial constraint.

| Stage | Baseline average | Approximate share |
| --- | --- | --- |
| Inbound sort | 1.46 min | 10% |
| Staging queue | 8.76 min | 60% |
| Scan / verify | 1.75 min | 12% |
| Load | 1.90 min | 13% |
| Depart | 0.73 min | 5% |

## Root-Cause Logic

| Why | Finding |
| --- | --- |
| Why are departures late? | Vans spend too long waiting before scan and load. |
| Why is the queue long? | All vans share one active staging and scan lane. |
| Why is capacity not opened earlier? | There is no real-time trigger or assigned peak response. |
| Why is response inconsistent? | Lane ownership and floater responsibilities are not standardized. |
| Why does the problem recur? | The process lacks a control mechanism and onboarding standard. |

Evidence boundary: The analysis validates the internal logic of the synthetic scenario. It does not prove that the same root cause exists in a real employer network.

# 4. Improve

## Six-Week Pilot at Station Alpha

The pilot uses weekly van-level observations and cumulative intervention states. It is designed as a practical operational pilot rather than a randomized experiment. Each stage has a defined change, observation count, guardrail review, and continue or stop decision.

| Week | Intervention state | Expected mechanism | Decision |
| --- | --- | --- | --- |
| 1 | Staggered starts | Reduce synchronized arrival surge | Continue |
| 2 | Add route-zone lanes | Create parallel flow | Continue |
| 3 | Stabilize lane ownership | Reduce response variation | Continue |
| 4 | Pre-stage high-volume routes | Shift work outside peak queue | Continue |
| 5 | Reassign two existing floaters | Protect lane capacity at peak | Continue |
| 6 | Full pilot standard | Confirm combined operating method | Adopt |

The cumulative design means the intervention effects are not fully separable. A real pilot should add a comparison shift or station, confidence intervals, and predetermined acceptance criteria before making a causal claim.

# 5. Rollout and Financial Case

## Rollout Governance

| Station | Window | Readiness gate | Local owner |
| --- | --- | --- | --- |
| Alpha | Weeks 1 to 6 | Pilot acceptance and guardrail review | Alpha Ops Manager |
| Beta | Weeks 7 to 8 | Training and lane configuration | Beta Ops Manager |
| Delta | Weeks 9 to 10 | Training and lane configuration | Delta Ops Manager |
| Epsilon | Weeks 11 to 13 | Site-specific layout and safety sign-off | Epsilon Ops Manager |
| Gamma | Weeks 14 to 16 | Peak-volume readiness review | Gamma Ops Manager |

## Component-Based Benefit Model

The revised business case avoids applying one assumed cost-per-package reduction to every package. It models three operational mechanisms, applies an 80% attribution factor, and subtracts implementation costs.

| Component | Annual gross benefit | Model logic |
| --- | --- | --- |
| Avoided delivery reattempts | $531K | Failure-rate reduction multiplied by packages, reattempt cost, and operating days |
| Reduced overtime | $212K | Minutes saved multiplied by route count, labor rate, and operating days |
| Reduced rescue routes | $70K | Six fewer rescues per day multiplied by rescue cost and operating days |
| Gross quantified benefit | $814K | Sum of modeled mechanisms |
| Attributable recurring benefit | $651K | Gross benefit multiplied by 80% attribution |
| Year 1 net benefit | $406K | Attributable benefit less $245K implementation cost |

| Case | Attribution | Recurring benefit | Year 1 net |
| --- | --- | --- | --- |
| Downside | 50% | $407K | $162K |
| Base | 80% | $651K | $406K |
| Upside | 100% | $814K | $569K |

Finance validation: Reattempt cost, rescue cost, labor rate, and implementation cost remain synthetic assumptions. A real rollout requires Finance approval and a benefits-realization owner.

# 6. Control

## Monitoring Mechanism

The business target and statistical control limits are intentionally separate. The target is 11.7 minutes. The center line and control limits come from stable post-rollout weekly observations, with limits set at the mean plus or minus three standard deviations of weekly means.

| Trigger | Response | Owner | Timing |
| --- | --- | --- | --- |
| Above target for two weeks | Review staffing, lane uptime, and volume mix | Station Ops Manager | Within 24 hours |
| Point beyond control limit | Investigate special cause and contain impact | Program Owner | Same day |
| Safety or scan-quality deterioration | Pause local standard and escalate | Safety or IT Lead | Immediate |
| Stable improvement for eight weeks | Review standardization and training update | Program Owner | Monthly review |

## Operating Cadence

| Mechanism | Purpose | Cadence | Output |
| --- | --- | --- | --- |
| Daily station huddle | Review target and guardrails | Daily | Local actions |
| Weekly business review | Validate metrics, risks, and dependencies | Weekly | Scorecard and action log |
| Network review | Review control signals and realized benefits | Monthly | Decisions and escalations |
| SOP review | Update process after confirmed change | Quarterly | Approved standard |

## Priority Risks

| Risk | Mitigation | Early signal |
| --- | --- | --- |
| Peak volume re-saturates lanes | Capacity scenario and reassignment plan | Queue time and lane utilization |
| Turnover erodes adherence | Training checklist in onboarding | Audit failure or rising variation |
| Scanner configuration delay | Configure one week before go-live | Failed readiness gate |
| Facility layout differences | Local site walk and safety sign-off | Unsafe or constrained flow |
| Change fatigue | Local owner, visible results, and closed action log | Missed actions or declining adherence |

# 7. Program-Management and Amazon Relevance

The value of the case study is the operating system around the analysis. It demonstrates how an engineering-style constraint diagnosis can be converted into a business case, rollout plan, governance structure, and repeatable operating mechanism.

| Capability | Evidence in this case study |
| --- | --- |
| Dive Deep | Van-level data, stage contribution, station segmentation, and explicit evidence boundaries |
| Bias for Action | Small weekly changes with continue or stop decisions |
| Ownership | One accountable sponsor, local owners, escalation rules, and benefit ownership |
| Deliver Results | Formula-derived operating outcomes and a conservative, auditable financial model |
| Earn Trust | Clear separation of synthetic data, public context, model outputs, and verified experience |

## References

Amazon Science. 2021 Amazon Last Mile Routing Research Challenge: Data Set. https://www.amazon.science/publications/2021-amazon-last-mile-routing-research-challenge-data-set

Companion files: Last_Mile_Delivery_KPI_Model_Revised.xlsx and Last_Mile_Delivery_Program_Overview_Revised.pptx.