## Slide 1
OPERATIONS PORTFOLIO
Last-Mile Delivery
Throughput Optimization
A DMAIC program case study built from synthetic van-level operating data
THE DECISION
Scale the operating changes only if service, labor, and safety guardrails hold in a live validation pilot.
Vishvanath
Program management and operations portfolio
Disclosure: all operating records and modeled benefits in this case study are synthetic.
01

## Slide 2
EXECUTIVE DECISION
A strong modeled result, with a clear validation boundary
02
DOCK-TO-DEPART
14.60 → 11.39 min
22.0% faster
ON-TIME DELIVERY
80.2% → 95.6%
+15.4 percentage points
OVERTIME
20.91 → 9.99 hr
52.2% lower per van-day
YEAR 1 NET
$406K
Base case after attribution
Recommendation
Adopt the standard-work package in a controlled site pilot. Release each rollout wave only after two stable weeks above the service target and within labor and safety guardrails.
What this does not prove
Synthetic observations show internal model behavior. They do not prove causality, customer impact, or transferable savings in a live station.

## Slide 3
EVIDENCE MODEL
Three evidence layers prevent overclaiming
03
1
Synthetic observations
7,450 deterministic van-day records across baseline, pilot, and post periods. Used to test definitions, calculations, segmentation, and controls.
2
Modeled outputs
Capacity and financial benefits are calculated from explicit assumptions. Attribution and implementation cost are shown separately.
3
Public context
Amazon Science route data informs terminology and scale context. It does not validate the synthetic results in this portfolio case.

## Slide 4
DEFINE
The program targets departure reliability, not route speed alone
04
Problem
Late van departures create compressed delivery windows, overtime exposure, and avoidable rescue activity.
Goal
Reduce average dock-to-depart time to 12 minutes or less while holding on-time delivery at 95% or better.
IN SCOPE
✓ Sort and stage
✓ Load and verify
✓ Dispatch release
✓ Exception response
GUARDRAILS
• Safety incidents do not increase
• Misloads stay at or below baseline
• No net headcount is added
• Customer promise is protected

## Slide 5
MEASURE
Measurement follows the van-day through five process stages
05
1
Sort complete
2
Staging queue
3
Load
4
Verify
5
Dispatch release
Operational definitions
Dock-to-depart: first loading scan to geofence departure
On-time delivery: delivered on or before promised timestamp
First-attempt failure: delivery not completed on initial customer visit
Data controls
Unique van-date key
Valid timestamp order
Required fields complete
Rates constrained to 0% to 100%

## Slide 6
ANALYZE
The staging queue is the largest controllable contributor
06
Share of excess dock time
Staging queue
60%
Load
16%
Verify
10%
Dispatch
8%
Sort handoff
6%
Root-cause logic
1. Vans wait after sort completion.
2. Staging locations are released in batches.
3. Release rules use fixed waves, not readiness.
4. Exceptions lack an owner and escalation time.
Root cause: batch-based staging and weak exception ownership.
The model treats this as a hypothesis to validate on-site, not as proven causality.

## Slide 7
IMPROVE
The pilot combines flow, visibility, and exception ownership
07
Readiness release
Release vans when carts, packages, and driver are ready, rather than waiting for a fixed batch.
Visual staging lanes
Use clear lane IDs and a single status board to reduce searching and handoff ambiguity.
Two flex roles
Reassign existing trained staff during the departure peak. The financial model includes their opportunity cost.
Exception clock
Assign one owner and a five-minute escalation point for missing package, device, and route issues.
Pilot design: two-week baseline, three-week intervention, then four weeks of post-period monitoring.

## Slide 8
PILOT AND POST RESULTS
The modeled improvement is broad, not dependent on one KPI
08
Metric
Baseline
Post
Change
Dock-to-depart
14.60 min
11.39 min
22.0% lower
On-time delivery
80.2%
95.6%
+15.4 pp
First-attempt failure
5.08%
3.28%
35.4% lower
Overtime per van-day
20.91 hr
9.99 hr
52.2% lower
Theoretical departure capacity rises 28.2% because capacity is inversely proportional to cycle time. This is not a forecast of packages delivered or customer demand.

## Slide 9
IMPLEMENTATION ROADMAP
Rollout uses readiness gates instead of a calendar promise
09
0
Validate
Weeks 0 to 2
Confirm timestamps, staffing assumptions, and baseline stability.
1
Pilot
Weeks 3 to 5
Run one departure wave with daily stand-ups and exception logging.
2
Stabilize
Weeks 6 to 7
Require two weeks above target with guardrails in control.
3
Scale
Weeks 8 to 12
Expand by wave, then by site, with a rollback owner named.
Gate to scale: on-time delivery ≥ 95%, dock-to-depart ≤ 12 minutes, no safety deterioration, and no increase in misloads.

## Slide 10
FINANCIAL MODEL
Benefits are component-based and adjusted for attribution
10
Avoided reattempts
$531K
Overtime reduction
$212K
Fewer rescue routes
$70K
Base case
$814K gross
× 80% attribution
= $651K recurring
− $245K implementation
$406K Year 1 net
Sensitivity range: downside $151K net | base $406K net | upside $692K net. Validate volumes, unit costs, and attribution before commitment.

## Slide 11
CONTROL
Business targets and statistical limits serve different purposes
11
Weekly dock-to-depart monitoring
Business target 12.0
W1
W2
W3
W4
W5
W6
W7
W8
Business target
A performance commitment. Escalate any week above 12 minutes.
Statistical limits
Calculated from stable process data. Investigate any point beyond a limit or any non-random run pattern.
Response owner: station operations manager | Review: weekly WBR | Rollback: two consecutive guardrail breaches

## Slide 12
PROGRAM GOVERNANCE
The mechanism turns analysis into accountable operating work
12
1
WBR
One page: KPI status, drivers, actions, owner, due date.
2
RACI
Sponsor: site leader. Accountable owner: operations manager.
3
RAID
Weekly review of risks, assumptions, issues, and dependencies.
4
Change control
Pilot change request required for scope, staffing, or target changes.
Escalation rule
Any guardrail breach gets an owner the same day. Two consecutive breaches pause expansion until root cause and recovery are reviewed.

## Slide 13
AMAZON AND PROGRAM-MANAGEMENT RELEVANCE
The project demonstrates mechanisms, judgment, and evidence discipline
13
Dive Deep
Trace a broad service problem to a specific staging and exception mechanism.
Ownership
Name one accountable operator, define response rules, and make rollback explicit.
Deliver Results
Connect operational KPIs to a phased rollout and component financial model.
Earn Trust
Separate synthetic evidence, modeled outputs, and public context in every claim.

## Slide 14
CLOSE
A credible next step is a live validation pilot
14
Decision
Proceed conditionally
The synthetic model supports the operating hypothesis and clarifies the mechanism. A real pilot must validate causality, safety, labor effects, and financial assumptions.
NEXT VALIDATION STEPS
✓ Validate event timestamps and missing-data rates
✓ Run one wave with a contemporaneous comparison
✓ Confirm flex-role opportunity cost
✓ Publish WBR owner and rollback criteria
Companion artifacts
KPI model workbook | DMAIC case study | Program overview